## Read me
Construction project management workbook: how to use it
One workbook per project. Sheets: Projects (phases and progress), Budget (worked out, do not type in the grey formula columns), Purchases, Labour, Daily log, Lists.
Rule 1: one row per event (an order line, a weekly pay run, a day). Never overwrite a row; add a correction row with a note.
Rule 2: every cost row names a phase exactly as written in Lists, or the Budget sheet will not count it.
Rule 3: one person owns each sheet. Others read it.
Rule 4: close each week: save a dated copy (Project-2026-W42.xlsx) and do not edit closed weeks.
Rule 5: delete the sample rows before you start.
Works in Excel and Google Sheets (SUMIFS, INDEX/MATCH, IFERROR).
From the Aaghaz360 guide: https://aaghaz360.com/guides/construction-project-management-excel-template/

## Projects
Phase | Planned start | Planned finish | Actual start | Actual finish | % complete | Status | Owner of the phase | Notes
Foundation |  |  |  |  | 100% | Done |  | Sample
Structure |  |  |  |  | 60% | Running |  | Sample
Finishing |  |  |  |  | 0% | Not started |  | Sample
External works |  |  |  |  | 0% | Not started

## Budget
Phase | Budget | Committed (ordered, not yet billed) | Spent: purchases billed | Spent: labour | Spent total | Left in budget | % of budget spent | % complete | Flag
Foundation | 8000
Structure | 34000
Finishing | 21000
External works | 6000
Total
Committed counts the part of each order not yet billed (simplified: order value − billed). Left in budget subtracts both spent and committed.
'Spending ahead of progress' shows when the share of budget spent is more than 10 points above % complete. Sample figures throughout.

## Purchases
Date | Phase | Cost type | Supplier | Item | Unit | Qty ordered | Rate | Order value | Qty received | Billed amount | Paid amount | PO no. | Status
sample | Foundation | Material | Supplier A (sample) | Concrete | m³ | 30 | 150 |  | 30 | 4500 | 4500 | PO-0101 | Paid
sample | Structure | Material | Supplier B (sample) | Steel bar 12 mm | t | 5 | 780 |  | 4.3 | 3354 | 3354 | PO-0142 | Part received
sample | Structure | Subcontract | Supplier C (sample) | Shuttering hire | job | 1 | 2600 |  | 0 | 0 | 0 | PO-0150 | Open

## Labour
Week ending | Phase | Trade / group | Days worked | Gross wages | Advances | Net paid | Approved by
sample | Foundation | Group of 5 | 30 | 3900 | 0 |  | Owner
sample | Structure | Mason, steel fixer, helper, crew | 43 | 788 | 140 |  | Owner

## Daily log
Date | Phase | Work done | Workers present | Material used | Problems / delays | Photos (link) | Reported by
sample | Structure | First-floor columns cast | 9 | Cement 22 bags | Rain stopped work at 3 pm |  | Site engineer

## Lists
Phases | Cost types | Suppliers | Trades
Foundation | Material | Supplier A (sample) | Mason
Structure | Labour | Supplier B (sample) | Steel fixer
Finishing | Subcontract | Supplier C (sample) | Helper
External works | Machines and services |  | Electrician
| Other |  | Plumber