## Purchase order
Purchase order
PO number | PO-0207 (sample)
Revision | 1 | Rev 1, Wed 15 Oct: cement 94 → 114 bags (stair flight)
Date issued | Tue 14 Oct
Project / site | Hillside House (sample)
Phase / work | Structure · first-floor slab
Requisition no. | MR-0118
Supplier | Supplier A (sample)
Quote reference / valid until | Q-311 · valid 14 days
Deliver to / receiver | Site store · storekeeper (site contact on the order)
Needed on site by | Thu 16 Oct, 7 am · deliveries 7 am to 4 pm
Part deliveries | Allowed · balance within 3 working days
Payment terms | 30 days from a correct bill matched to the order and delivery notes
Line | Item and specification | Unit | Quantity | Rate | Amount
1 | Cement, 50 kg bag, type per specification | bag | 114 | 9.4
2 | Steel bar 12 mm, grade per drawing S-04 | t | 1.5 | 770
3 | Steel bar 10 mm, grade per drawing S-04 | t | 0.6 | 780
4 | Binding wire | kg | 15 | 1.6
5
6
7
8
9
10
11
12
Subtotal
Delivery to site |  |  |  |  | 45
Total before tax
Tax rate (sample; use your own) |  |  |  |  | 5%
Tax
Total
Terms (summary; agree full terms with your supplier)
Quote PO number and line on every delivery note and bill.
Deliver to the address above in the hours stated; the receiver signs for counted quantities only.
Short, damaged or wrong items may be rejected at delivery; rejected items are not paid for.
No substitutions or price changes without a written revision of this order.
Steel deliveries come with the mill or test certificate the specification asks for.
Authorised by, date
Accepted by supplier, date
Sample figures, not market rates. Amount = quantity × rate. Rev 1 is the current version; keep Rev 0 in the PO log.

## Deliveries
Deliveries against the order
Delivery note | Date | PO line | Delivered | Rejected | Accepted | Reason for rejection
DN-5512 | Thu 16 Oct | 1 | 60 | 0
DN-5512 | Thu 16 Oct | 2 | 1.5 | 0
DN-5512 | Thu 16 Oct | 4 | 15 | 0
DN-5530 | Fri 17 Oct | 1 | 54 | 2 |  | 2 bags torn, photographed
DN-5530 | Fri 17 Oct | 3 | 0.6 | 0
Outstanding by line
PO line | Item | Ordered | Accepted to date | Outstanding | Accepted value
1
2
3
4
5
6
7
8
9
10
11
12
Accepted value, before delivery and tax
Pay the bill for accepted quantities. Anything outstanding stays open on the order until it arrives or the order is revised.

## PO log
Purchase order log
PO no. | Rev | Date | Project | Phase | Supplier | Requisition | Total | Needed by | Status | Bill no. | Notes
PO-0207 | 0 | Tue 14 Oct | Hillside House | Structure | Supplier A | MR-0118 | 2704.38 | Thu 16 Oct | Replaced by Rev 1 |  | Sample row
PO-0207 | 1 | Wed 15 Oct | Hillside House | Structure | Supplier A | MR-0118 | 2901.78 | Thu 16 Oct | Part delivered · 2 bags open |  | Cement 94 → 114 bags