## Cost to complete
Cost to complete report · Hillside House (sample) · cost budget by phase
Phase | Budget | Actual to date (paid + billed) | Committed, not yet billed | Still to commit | Cost to complete | Forecast at completion | Variance (+ under / − over) | % complete (measured) | Earned value | Budget left
Foundation | 38000 | 39200 | [5 empty] | 100%
Structure | 72000 | 51600 | [5 empty] | 70%
Services | 34000 | 4800 | [5 empty] | 10%
Finishes | 56000 | 0 | [5 empty] | 0%
Total
Margin
Contract value with the client | 230000
Planned margin (contract − budget)
Forecast margin (contract − forecast at completion)
Planned margin %
Forecast margin %
Three methods compared (whole project)
A. Budget left: budget − actual
B. Bottom-up: committed + still to commit
C. Cost performance index (CPI = earned value ÷ actual)
C. Performance-based forecast at completion: budget ÷ CPI
C. Performance-based cost to complete: forecast − actual
Sample figures. Enter actual cost from paid and billed amounts; committed and still-to-commit come from the two other sheets. Use the same phase names on every sheet.

## Open commitments
Open commitments: approved orders and subcontracts not yet billed
Phase | Order / contract | What | Value not yet billed
Structure | PO-0219 | Blocks, delivered, not yet billed | 4100
Structure | SC-004 | Steel fixing subcontract, balance | 2300
Services | SC-006 | Electrical subcontract, balance | 12000
Finishes | PO-0231 | Doors and windows order, balance | 3000
Include deliveries received but not yet billed. Remove a line when its bill is entered as actual cost.

## Still to commit
Still to commit: work not yet ordered or let, at today's rates
Phase | Item | Unit | Quantity left | Current rate | Amount
Structure | Roof slab concrete | m³ | 40 | 145
Structure | Steel bar | t | 5 | 780
Structure | Formwork hire | lot | 1 | 2300
Structure | Labour | worker-day | 110 | 50
Services | Electrical second fix (not yet let) | lot | 1 | 9000
Services | Plumbing fixtures | lot | 1 | 7500
Finishes | Floor and wall tiles | m² | 180 | 40
Finishes | Painting, labour and material | lot | 1 | 9800
Finishes | Doors and windows, rest of package | lot | 1 | 21000
Finishes | Kitchen | lot | 1 | 12500
Finishes | Plastering labour | worker-day | 80 | 50
Quantities come from the drawings or BOQ minus what is already built or ordered. Rates are today's quotes, not the estimate.