## Requisition
Material requisition
Requisition no. | MR-0118 (sample)
Project / site | Two-storey house (sample)
Phase / work item | First-floor slab and beams
Requested by | Site engineer
Date raised
Needed on site by
Deliver to / receiver | Site store · storekeeper
Reason / drawing or BOQ ref. | Slab pour planned for Saturday
Item and specification | Unit | Quantity needed | In site store now | Already on order | To issue from store | To buy | Est. rate | Est. amount
Steel bar 12 mm, grade per drawing | t | 1.8 | 0.3 | 0 |  |  | 780
Steel bar 10 mm, grade per drawing | t | 0.6 | 0 | 0 |  |  | 790
Cement, 50 kg bag | bag | 140 | 46 | 0 |  |  | 9.5
Binding wire | kg | 25 | 10 | 0 |  |  | 1.6
Total estimated value
Phase budget left before this request | [7 empty] | 3400
Budget left after this request
Approval limit of the project manager | [7 empty] | 1500
Who approves
Decision (approved / changed / returned)
Approved by, date and time
Note from approver
Sample figures, not market rates. Check the store and open orders before you buy; 'To buy' = needed − in store − on order.

## Register
Requisition register
MR no. | Date raised | Project | Phase | Raised by | Needed by | Est. value | Approver | Decision | Decided on | PO no. | Delivered on | Status | Notes
MR-0118 |  | Two-storey house | First-floor slab | Site engineer |  | 2561 | Owner | Approved |  | PO-0203 |  | Ordered | Sample row